Action plan for regional cooperation on chemicals and waste management

Latin America and the Caribbean

2019-2020 Biennium

Final Draft August 2018

Action plan for regional cooperation on chemicals and waste management

Latin America and the Caribbean

2019-2020 Biennium

Final Draft August 2018

Contents

Message from the Chair and Vice-chair of the Chemicals and Waste Network Steering Committee	3

Background	5

Situational analysis in Latin America and the Caribbean and contextualization of the Action Plan	7

Action Plan objectives and priority issues	11

Action Plan (2019-2020)	14

Contributions to the implementation of the 2030 agenda	27

Resources for implementation	27

Monitoring and follow-up	28

# Message from the Chair and Vice-chair of the Chemicals and Waste Network Steering Committee

Our vision as a Network for the Latin America and Caribbean region is to minimize the adverse effects of chemicals and waste on the health of the populations within the region and the environment. The mandate and main objective that we have as a Network is to support the coordination and cooperation among countries in the region in order to achieve the 2030 Agenda Sustainable Development Goals on the sound management of chemicals and waste.

The Intergovernmental Network for Latin America and the Caribbean (“the Network”) developed this 2019-2020 Biennium Action Plan as a roadmap for the next two years to work on moving towards our objective. The Plan has been developed through an inclusive and participatory consultation process in which national focal points deliberated on key priority issues in each country with relevant stakeholders, providing input to the Network through a comprehensive survey. The Plan also takes into account developments under the chemicals and waste agenda at the international level.

The Action Plan has been developed in line with the following principles that the Network identified as relevant:

Cooperation – The Latin America and Caribbean Forum of Ministers of Environment believe that a cooperation agenda in the region will help in scaling up efforts by countries to tackle key challenges on chemicals and waste management. The Network and this Action Plan are focused on supporting cooperative actions that can enhance and improve specific national actions.

Inclusiveness – The chemicals life cycle touches every sector of our societies, so the Network acknowledges the key role of all stakeholders and sectors related to the chemcials and waste management agenda, promoting their active participation and engagement on the decision-making process, so they can have a clear and broad understanding of the challenges as a region and work together on the solutions.

Complementarity – The Plan builds upon on-going efforts within the region and tries to avoid any duplication with activities that are already in place. The Network instead intends to continue, coordinate with, and enhance any on-going initiative on key priority issues.

Feasibility – The Plan has been kept as realistic as possible, keeping a limited but prioritized number of activities that are feasible for the next two years depending on the resources available to support the work of the Network and the region.

We look forward to working with countries and stakeholders of the region to implement this Action Plan and to advance together towards a better and safer environment. We would like to express our sincere appreciation to all who assisted us in crafting this Action Plan as well as the partners engaged in its implementation.

Leticia Carvahlo		                                Andrea Jones Bennett

Chair				             Vice-chair

Chief of Environmental Quality Branch	        Director, Projects and Enforcement

Ministry of Environment                 Environment and Risk Management Branch

Ministry of Economic Growth and Job Creation

Brazil 				              Jamaica

# Background

At the XX Meeting of the Forum of the Ministers of the Environment of Latin America and the Caribbean held in Cartagena, Colombia, which was held from the 28 to 31 of March 2016, Ministers and Heads of Delegations endorsed the “Declaration of Cartagena”, which agreed, inter alia:

- To reaffirm the necessary coordination and cooperation of actions and consistent initiatives between countries of Latin America and the Caribbean, according to the national circumstances and priorities;

- To recognize that the sound management of chemicals and waste is key for the protection of human health and environment and encourage the region to adopt actions to minimize the impact of chemicals production and use and generation of waste, especially for most vulnerable populations; and

- To reaffirm the importance to promote the cooperation and coordination between Conventions about chemicals and hazardous waste management and the implementation of the 2030 Agenda.

By decision (No. 8) on Chemicals and Waste, the XX Forum established an Intergovernmental Network for Latin America and the Caribbean, which comprises focal points from governments and other related stakeholders. The Network has the following objectives:

General objectives:

- Contribute to the implementation of the 2030 Agenda for Sustainable Development by facilitating the achievement of the chemicals and waste-related goals and targets by Latin America and the Caribbean (LAC);

- Support the implementation of the chemicals and waste-related international agreements in the countries of the region;

- Strengthen regional cooperation and facilitate exchange of information and best practices on the sound management of chemicals and wastes;

- To promote technology transfer mechanisms and capacity building for the reduction of the use of chemicals; and

- Provide recommendations at policy and programme level for consideration of the Forum of Ministers of Environment of Latin America and the Caribbean.

Specific objectives:

- Support the development and implementation of a regional Action Plan on chemicals and waste in the region of Latin America and the Caribbean region, in coordination with other relevant initiatives and stakeholders;

- Identify and share information among the countries of the region financing opportunities and support resource mobilization to undertake activities related with the area of chemicals and waste;

- Facilitate the strengthening of capacities and sharing of information/data, experiences, policies, projects and good practices on the sound management of chemicals and waste among the countries of the region and with other regions, including through south-south cooperation actions and engaging different stakeholders, and with the support of the network of regional and sub-regional centers of the Basel and Stockholm Conventions;

- Promote the knowledge generation and research activities within this area;

- Promote awareness raising and dissemination of information on risks and impacts linked to chemicals and waste;

- Identify priorities, challenges and opportunities, and make recommendations for the consideration of the LAC Forum of Ministers of Environment and other relevant forums;

- To support the development of information sharing mechanisms in work areas such as: contaminated sites, mercury management in river ecosystems, reduction and eventual elimination of mercury use in artisanal mining, among others; and

- Contribute to other objectives on chemicals and waste management of the Forum of Ministers of Envrionment of the LAC region.

A Steering Committee of the Network was established according to the terms of reference of the Network, comprising two members from each of the sub-regions of Latin America and the Caribbean (Mesoamerica, Caribbean, Andean and the Southern Cone). The Steering Committee led the development process of this 2019-2020 Biennium Regional Action Plan, with support of a Working Group that was established as per Decision 8 of the Forum of Ministers, and in collaboration with all the Network’s national focal points.

In order to identify the priority areas for cooperation within the region and to facilitate the development of the Plan, in 2017 the countries of the region were consulted through the administration of a survey instrument by their respective national focal point to: (i) identify priority issues, (ii) ascertain their importance at a national level (ranking), and (iii) the cooperation actions that the Intergovernmental Network could pursue to support countries on addressing the priority issues. Twenty-three (23) countries, representing 70% of the region, answered the survey, and the responses received have been informed for the development of this Action Plan.

# Situational analysis in Latin America and the Caribbean and contextualization of the Action Plan

Economies in Latin America and the Caribbean are dependent on sectors that involve intensive chemicals consumption, such as agriculture, mining, oil industry and manufacturing. For example, the Latin America region represents 19 per cent (19%) of global expenditure on pesticides according to the Global Chemicals Outlook (2013). Additionally, some countries in the region have primary production of chemicals, such as Argentina, Brazil, Chile and Mexico (and at a smaller scale in other countries). Secondary production of chemicals is more commonly seen in the region though, such as the formulation of pesticide mixtures and production of household and cosmetic products. Much of this manufacturing is undertaken by Small and Medium-sized Enterprises (SMEs), which usually do not have a clear strategy or knowledge of sound management of chemicals and waste. A 2010 survey by the World Bank Group estimated that 91 per cent (91%) of the firms in the region are SMEs.

Governance

Legal and institutional frameworks on chemicals and waste are not rare in the region. Most of the countries already have an extensive legal framework on different aspects of chemicals and waste management and the respective competent authorities to enforce it. The challenge for these countries is the lack of an integrated approach to address chemicals and waste priority issues, as legal instruments and mandates are being executed by several competent authorities, sometimes in an uncoordinated manner. This poses a challenge for the enforcement of chemicals and waste management regimes, resulting in specific activities or types of chemicals being highly regulated (e.g. chemicals used in agriculture), while for others there is no specific regulation. In addition, the diverse number of competent authorities may also pose a problem in the distribution of scarce national resources and an effective coordination and communication for the sound management of chemicals and waste.

There are already important strides being made in the region, towards instituting integrated frameworks for the sound management of chemicals. Some examples are the national policies on chemicals and hazardous waste in Guatemala, Honduras and Nicaragua or the promulgation of Pesticides and Toxic Chemicals legislation in several Caribbean countries, such as Saint Kitts and Nevis, Saint Lucia, and Trinidad and Tobago. Other countries, such as Argentina, Brazil and Colombia, are in the process of preparing comprehensive regulations or programs to register and control industrial chemicals. Another important effort is the creation of coordinating groups or advisory committees that include stakeholders from all key sectors and institutions mandated or relevant to chemicals and waste management. Some countries have official coordinating groups with specific mandates and rules of procedure. In other countries the group exists, but on an ad hoc basis to address specific chemical-related issues, for example national working groups to support the development of the Stockholm Convention National Implementation Plans (NIP), Minamata Initial Assessments and National Action Plans for Artisanal and and Small Scale Gold Mining (ASGM). It has been observed that an effective enforcement of the chemicals and waste legal framework is more evident in countries that have this kind of coordination mechanism, although other challenges may surface such as the lack of resources, the complexity of the topics to be addressed, the excessive workload of technical officers, among others.

Mainstreaming is a priority within the region. Several countries have implemented projects on mainstreaming to integrate the sound management of chemicals into development planning, development strategies and national budgets. More recently, countries are working now on scaling up mainstreaming activities to support the implementation of the Sustainable Development Goals (SDGs) relevant to chemicals and waste management. Countries are still building capacities and identifying the most efficient manner to achieve this.

National and regional capacities

Although capacities and knowledge exists among countries of the region, there are still gaps in the management of certain aspects of the chemical lifecycle.

Chemicals registration in the region is done at the national level through various and isolated procedures, which are not always linked to an electronic database. For example, the registration of pesticides or the register of imported chemicals is done in many countries, but the process may not be supported by a simple and online database, with information/data that could be accesible to the public. Pollutant Release and Transfer Registers (PRTRs) are important tools that are being considered or implemented by several countries of the region. Recently, several countries are taking steps to enter the Organization for Economic Co-operation and Development (OECD), which recommends the establishment of such a system. Countries could establish their PRTRs by integrating and improving different platforms and registration systems they already have in place, but capacities to achieve this need to be strengthened. The region already has pioneer PRTR systems, such as those of Chile and Mexico, which could serve as a model for replication in other countries of the region.

Chemicals storage and transport is still not completely controlled in the region. The use of Material Safety Data Sheets (MSDS) is not mandatory in many of the countries. The Globally Harmonized System for the Classification and Labelling of Chemicals (GHS) is well known in the region, but its effective implementation has not yet been achieved. Countries such as Argentina, Brazil and Mexico that are already in the process of implementing the GHS and many other countries of the region are preparing to do so. However, these are isolated initiatives, while such a harmonized system provides the opportunity for a well-coordinated and effective implementation at the regional level, adapting it to the specific needs of the region. A poor prevention and response to chemical accidents and spills in the region is probably linked to the missing regulations and enforcement of the sound storage and transport of hazardous chemicals.

The assessment and revision of tariff coding for chemicals under Customs is also an area with an opportunity for improvement. For example, the recent entry into force of the Minamata Convention on Mercury and the growing interest on improving mercury management has highlighted the fact that mercury-containing products, as listed under the Convention, are not well identified by Customs authorities. These products are generally quantified or inventoried as bulk items, therefore this is non-accurate data on the number of products entering or leaving a country or the quantity of mercury or mercury compounds contained in each product. The same happens for products with persistent organic pollutants (Stockholm Convention), a problem that has been highlighted with the inclusion of new chemicals in the Annexes of the Stockholm and the Rotterdam Convention. This makes it difficult to ascertain the true situation regarding these products in the region.

A significant challenge in the region is the control of chemicals illegal traffic. Most of the countries do not yet have the capacities to control the illegal traffic of chemicals at the national level, and furthermore, the region is not yet in a position to address the transboudary issue in a coordinated manner. The most common cases in the region of this kind of trafficking are pesticides banned under the Stockholm Convention or mercury used for artisanal and small-scale gold mining (ASGM).

Regarding integrated waste management, there are still challenges with effective enforcement of regulations, institution of self-sustaining municipal waste management services, and an effective control and sound management of hazardous waste in several countries. Priority concerns that have been identified in various countries of the region include: (i) the lack of waste inventories and capacities to develop it; (ii) the lack of/inadequate waste seggregation in most of the countries (a lot of the waste collected is separated by the informal sector), and household and hazardous wastes transported together to landfills; (iii) weak or non-existent infrastructure and technologies for the treatment and final disposal of hazardous waste, and (iv) the still common practice of open-burning of waste.

International conventions and agreements

Annex I shows the current status of ratificiation of chemicals and waste related international conventions in the LAC region. Although the ratification rate in the region is high, countries are not yet fully equipped with the necessary technical knowledge and/or expertise to effectively address the chemicals regulated under the respective Conventions, neither is there sufficient personnel engaged in the technical branches to specifically oversee the sound implementation of these Conventions. This situation is aggravated due to the constant turnover of personnel and changes of administration within the competent authorities. There is therefore a priority to mainstream the implementation of the Conventions into national plans and budget.

Other priorities for the region include building laboratory capacities and infrastructure in order to facilitate the analysis of POPs, Mercury, and other heavy metals, as well as other chemicals of concern at a local level; and building capacities to apply the Best Available Techniques (BAT) and Best Environmental Practices (BEP) regarding POPs unintentionally released by industry.

With respect to the Minamata Convention, the region has a significant challenge with respect to the regulation of mercury use in the Artisanal and Small-Scale Gold Mining (ASGM) sector. This activity has recently expanded to many countries within the region and in some cases entails methods of amalgamation with mercury. A regional report on implementation of the Minamata Convention estimates that ASGM is present in at least a dozen countries of the region, and that approximately 500,000 artisanal miners are involved in ASGM activities. This report estimates that the region accounted for 29 per cent of the global mercury emissions from ASGM in 2010. These activities are poorly controlled, while thousands of miners and adjacent populations and ecosystems are adversely affected. In addition, these activities may be also an important source of mercury illegal trade.

A key cross-cutting issue that relates to the implementation of the international conventions and the sound management of waste in general, is the still unsafe methods and lack of the appropriate infrastructure for the interim storage and final disposal of hazardous waste. Such is the case for mercury waste stocks, which are expected to increase significantly in the region with the implementation of the Minamata Convention. However, an interim storage facility in the region is yet to be identified.

# Action Plan objectives and priority issues

The main objective of this Action Plan is to identify the priority areas for cooperation and actions at the sub-regional and regional levels to enhance implementation of the chemicals and waste management agenda in the Latin America and Caribbean region and to contribute to the implementation of the 2030 Agenda for Sustainable Development and the SAMOA Pathway.

In support of this objective and taking into account the results from the survey admininstered by the national focal points of the Network, the following structure is proposed under the Action Plan:

- Priority topics (work areas for the Network)

- Priority sub-topics (strategic priorities to be addressed during the 2019-2020 biennium under each priority topic)

- Specific actions to be undertaken during the 2019-2020 biennium (activities and tasks by the Network to address the strategic priorities)

A summary of the Sustainable Development Goals and targets to which this Action Plan relates is also provided.

The specific actions listed in the Action Plan are intended to foster regional cooperation and are therefore actions that promote or facilicate work among countries, cooperative resource mobilization, among others. The type of cooperative actions to be implemented was also highlighted from the responses to the survey. The following were the actions identified for action within the 2019-2020 biennium:

- Resource mobilization (identify and facilitate access to financial resources)

- Face-to-face trainings/workshops

- Support for the development of project proposals

- South-South exchange programme, i.e. sharing of technical expertise, including human resources, sharing of best practices and lessons learnt, study tours, etc.

Other types of cooperative activities are also considered in this Action Plan:

- Development of guidance and tools

- Online training modules

- South-South cooperation for technology transfer

- Undertake regional assessments on specific issues of concern

- Webinars

- Regionally-coordinated education and awareness-raising programmes

- Develop regional or sub-regional strategies and action plans on specific issues of concern

The six priority topics under the Plan include two crosscutting issues (governance and information) and other more specific topics that require immediate action as per mandate by the Forum of Ministers of Environment of the region:

Governance, coordination mechanisms and international presence

Strengthening the legal and institutional frameworks at the national and regional level to facilitate the coordinated and integrated management of chemicals, as well as ensuring that regional priority issues or concerns related to chemicals and wastes are advanced and actively pursued in the chemicals agenda at the international level.

Governance, coordination mechanisms and international presence

Strengthening the legal and institutional frameworks at the national and regional level to facilitate the coordinated and integrated management of chemicals, as well as ensuring that regional priority issues or concerns related to chemicals and wastes are advanced and actively pursued in the chemicals agenda at the international level.

Knowledge, information and monitoring

Improving the availability of information and data on chemicals and waste at the national and regional levels, including information dissemination to the civil society.

Knowledge, information and monitoring

Improving the availability of information and data on chemicals and waste at the national and regional levels, including information dissemination to the civil society.

Priority topics under the SAICM Global Plan of Action

Sound implementation of SAICM, in accordance to the Global Plan of Action and addressing the Emerging Policy Issues.

Priority topics under the SAICM Global Plan of Action

Sound implementation of SAICM, in accordance to the Global Plan of Action and addressing the Emerging Policy Issues.

Basel, Rotterdam and Stockholm Conventions

Implementation of the international conventions on chemicals and waste, building national capacities to comply with international obligations under these three conventions.

Basel, Rotterdam and Stockholm Conventions

Implementation of the international conventions on chemicals and waste, building national capacities to comply with international obligations under these three conventions.

Mercury and Lead

Addressing chemicals of global concern, particularly mercury and lead, in an integrated and coordinated manner, with the final goal being to significantly reduce their presence in the environment and their adverse effects in human health, as well as facilitating implementation of the Minamata Convention on Mercury.

Mercury and Lead

Addressing chemicals of global concern, particularly mercury and lead, in an integrated and coordinated manner, with the final goal being to significantly reduce their presence in the environment and their adverse effects in human health, as well as facilitating implementation of the Minamata Convention on Mercury.

Waste management

Integrated management of the different types of waste, at the national and the regional levels.

Waste management

Integrated management of the different types of waste, at the national and the regional levels.

The sub-topics that will be addressed under the 2019-2020 Action Plan under each main topic are the following:

| Governance, coordination mechanisms and international presence | - Review and strengthen chemicals and waste legal and institutional frameworks - Mainstreaming of chemicals and waste into national strategies and plans for sustainable development, as well as in national budgeting processes |
| --- | --- |
| Knowledge, information and monitoring | - Establish methodologies and institutional regimes for health and environmental risk assessment and management of chemicals and waste, including promotion of relevant legal cooperation - Strengthening capacities of national laboratories with respect to sampling and analysis of POPs and other priority chemicals in water, air, soil and products - Support the development of national registers for chemicals e.g. Pollutant Release and Transfer Registers (PRTR), National Chemical Inventories or Electronic Manifest Tracking System for Chemicals - Awareness-raising of the civil society about the adverse effects in human health and the environment of chemicals that are included in the Basel, Rotterdam, and Stockholm Conventions and as part of the Emerging Policy Issues under SAICM (EPIs) |
| Priority topics under the SAICM Global Plan of Action | - Building capacities of healthcare personnel to identify and prevent poisoning and diseases related to chemical exposure - Promote implementation of the GHS, including the appropriate enforcement mechanisms - Build capacities to prevent and effectively respond to chemical accidents and spills - Identification and remediation, where posible and feasible, of contaminated sites |
| Basel, Rotterdam and Stockholm Conventions (BRS) | - Implement Best Available Techniques (BATs) and Best Environmental Practices (BEPs) with respect to unintentional POPs emissions - Build capacities to prevent and regulate illegal traffic of chemicals and waste |
| Mercury and lead | - Management of mercury waste (collection, storage, treatment, disposal), giving special attention to waste products containing mercury - Develop strategies and plans to reduce and, when feasible, eliminate the use of mercury in ASGM - Establish/strengthen mechanisms to control legal and illegal trade of mercury and mercury compounds - Improve public knowledge and awareness of the health and environmental impacts of one of these priority substances (mercury/lead) |
| Waste management | - Develop systems to reduce, measure and characterize waste generation, including hazardous waste, maintain updated national waste inventories, and enhance waste management strategies - Promote best practices and best technologies to implement integrated management of hazardous waste (e.g. e-waste, used oils, used lead acid batteries, biomedical waste, and obsolete highly hazardous pesticides) - To support actions for the sound management of lead in products |

# Action Plan (2019-2020)

The following Plan outlines the regional cooperative activities, resources required to effectively implement those activities, as well as the associated timeframes:

| Topic 1: Governance, coordination mechanisms and international presence |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-topic | Cooperative actions | Milestones | Main SDG target to which action contributes | Timeframe | Responsible/Partners | Resources required |
| 1.1 Review and strengthen chemicals and waste legal and institutional frameworks | 1.1.1 Host a webinar to disseminate existing initiatives on integrated chemicals management policies, regulations, financing and cost recovery, and coordination mechanisms among the Network focal points | Existing integrated chemicals management policies and regulations have been identified and disseminated in all sub-regions | 12.4 17.14 | 1 webinar held in February 2019 | Network focal points, Ministries of Environment, Ministries of Health, legal drafters from Ministries, UN Environment ROLAC, UN Envrionment Legal Office, Regulatory Group of Chemical Industry | Countries willing to share their experiences Webinar platform |
|  | 1.1.2 Undertake regional education and awareness raising , including presentation at high level events, on the benefits of developing integrated legal frameworks and strenthening the institutional framework for the sound management of chemicals and waste, as well as the mainstreaming into the development agenda and budgeting processes | A factsheet and/or infographic (available information can be tailored to the region situation) Include on the Agenda for the Forum of Ministers of Environment an ítem on integrated and strengthened legal and institutional frameworks, and mainstreaming chemicals and waste management into national development plans, strategies and budgets | 12.4 17.14 | During inter-sessional meeting of the Forum of Ministers of Environment in 2019 | UN Environment ROLAC, the Network’s Steering Committee, LAC country(ies) presenting case studies | Resources to design/develop education and awareness raising material and tools Resources for event logistics |
| 1.2 Mainstreaming chemicals and waste into national strategies and plans for sustainable development, as well as in national budgeting processes | 1.2.1 Identification of funding and Project options on mainstreaming and promoting goals contained in the SDGs related to chemicals management | Two project proposals (national or regional proposals) have been developed (e.g. Special Programme, GEF) | 12.4 17.14 | 1 proposal July-December 2019 1 proposal July-December 2020 | Network focal points, UN Environment, UNDP and other agencies working on mainstreaming, BRS Regional Centres | Contact with key agencies working on mainstreaming Resources to develop the project proposals |
|  | 1.2.2 To host a webinar on best practices in mainstreaming of sound chemicals and waste management into national development plans, strategies and budgeting processes | Best practices, including from other regions, have been compiled in a short report and disseminated in all the region | 12.4 17.14 | 1 webinar by June 2019 | Network focal points, Ministries of Environment, Ministries of Health, UN Environment ROLAC, BRS Regional Centerls | Countries willing to share their experiences Webinar platform Consultancy for compilation report |

| Topic 2: Knowledge, information and monitoring |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-topic | Cooperative actions | Milestones | SDG and target to which action contributes | Timeframe | Responsible/Partners | Resources required |
| 2.1 Establish methodologies and institutional regimes for health and environment risk assessment of chemicals and risk management of chemicals and waste, and promote relevant legal cooperation | 2.1.1 To organize a comprehensive regional training on institutional methodologies for risk evaluation (health-environment). | A regional training programme has been developed with the collaboration of relevant academia and public entities from the region and countries of other regions. The training includes a session on regional cooperation, exchange on national approaches, and options for mutual acceptance of data from risk assessments. A compilation of a list of institutions with experience in risk assessments and risk management in the region will be prepared to facilitate the training. The regional training succesfully delivered (online or face-to-face). Participants have a methodological framework to assess chemical risks to human health and the environment. | 12.4 3.9 6.3 17.6 | Programme designed by December 2019 One training session delivered by May 2020 | The Network Steering Committee, UN Environment ROLAC, PAHO, FAO, BRS and Minamata Secretariats, SETAC. KEMI, contributing countries. Private sector. | Resources to develop the training programme. Resources to hold a training event (or online training) Countries and partners willing to be trainers and trainees |
|  | 2.1.2 To promote a postgraduate training programme on chemical risk assessment with participation of WHO, UN Environment, US EPA, OECD, KEMI, CETESB, industry and academia | Relevant partners and academia working on risk assessment in the region are identified and collaborate to design the training programme. | 12.4 3.9 6.3 17.6 | Relevant partners identified by June 2019 Programme designed for February 2020. | Governmental and Network focal points, US EPA, OECD, KEMI, CETESB, SETAC, UN Environment, IOMC agencies | Contact with key agencies and partners. Resources to design the training programme. |
| 2.2 Strengthening capacities of national laboratories on sampling and analysis of POPs and other priority chemicals in water, air, soil and products | 2.2.1 Dissemination of information on existing initiatives in the region related to the strengthening of laboratory capacities for sampling and analysis of POPs | Results and outputs (methodologies, protocols) obtained from on-going projects in the region (e.g. GMP Phase II and MERCOSUR project) are made available to all LAC countries, including a list of laboratories in the region | 12.4 3.9 6.3 17.6 | Initiatives disseminated throughout 2019-2020 | Governmental and Network focal points, BRS Regional and sub-regional Centres, UN Environment, Stockholm Convention Secretariat | Countries willing to share their experiences |
| 2.3 Support the development of national registers of chemicals e.g. Pollutant Release and Transfer Registers (PRTR), National Chemical Inventories or Electronic Manifest Tracking System for Chemicals (life cycle data recording and management mechanism) and chemical inventories | 2.3.1 Identification of funding and Project options to promote South-South cooperation in the development of national chemical registers, chemical inventories and inventories of new POPs | List of substances commonly considered in the registers is developed (to take into consideration lists previously identified in other regions, such as the OECD Global PRTR Substantes List) Two cooperation Project proposals have been developed | 12.4 and 12.6 3.9 6.3 16.6 and 16.7 | Proposals developed by June 2020 | Network focal points, UN Environment ROLAC | Resources to develop the proposals |
| 2.4 Awareness raising of the civil society about the adverse effects to human health and the environment of chemicals included in the Basel, Stockholm and Rotterdam Conventions and the Emerging Policy, and about the responsibilities for the management of those chemicals | 2.4.1 To undertake information dissemination campaigns, taking into account: • Issues of importance for groups of countries with a same language; • The target populations of those information campaigns; • Information materials that are available and that should be developed; •Partners interested in supporting educiation and information campaigns (in addition to authorities, NGOs, industry, academia, etc). | The information dissemination campaign has been designed. | 12.4 and 12.8 6.3 | At least one campaign desgined by June 2019 At least one campaign undertaken by December 2020, at the national level or a joint regional campaign (In addition to what is indicated in activity 5.4.1, Topic 5 on mercury and lead) | Network focal points, UN Environment ROLAC | Personnel and resourcess to design and undertake the campaign |

| Topic 3: Priority topics under the SAICM Global Plan of Action |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-topic | Cooperative actions | Milestones | SDG and target to which action contributes | Timeframe | Responsible/Partners | Resources required |
| 3.1 Building capacities of healthcare personnel to identify and prevent poisoning cases and diseases related to chemical exposure | 3.1.1 Convene a face-to-face workshop with key stakeholders from each country (from healthcare sector) to elaborate a program to improve prevention of poisoning and exposure in the region (including key stakeholders in the emergency response and disaster preparedness sectors). Utilization of train-the-trainers approach. | A regional program for the identification and prevention of poisonings is present Healthcare and emergency preparedness personnel in the region has a better understanding and is better prepared to prevent poisonings and chemical exposure | 3.8 and 3.9 | By May 2019 | National focal points, key stakeholders from the healthcare sector, WHO, PAHO, UN Environment | Resources for workshop logistics and travel National resources to implement the programme |
|  | 3.1.2 To develop awareness raising material for healthcare personnel and the civil society (which can be used in the whole region) | Easy-to-follow videos about poisoning and exposure, risks associated with some products related to SAICM Emerging Policy Issues and electronic waste. | 3.8 and 3.9 16.7 | At least 2 videos uploaded in a Network website by March 2020 | Network focal points with support of WHO, PAHO, international NGOs, SAICM Secretariat, UN Envrionmental Chemicals Branch | Resources to design, develop and upload the material Network website |
| 3.2 Promote implementation of the GHS, including the appropriate enforcement mechanisms | 3.2.1 Convene a webinar on GHS and to share GHS implementation experiences in the region, including experiences on enforcement mechanisms | GHS experiences in the region have been shared | 12.4 and 12.6 3.9 | By June 2019 | Network focal points, Ministries of Environment, Ministries of Health, Customs, Ministries of Labour, UN Environment ROLAC, UNECE | Countries willing to share their experiences Webinar platform |
|  | 3.2.2 Convene a face-to-face regional training for Customs officers and other stakeholders on harmonizing tariff codes. Training of trainers approach and exchange of experiences. | Customs authorities within the region are prepared to implement national activities on harmonizing tariff codes | 12.4 16.6 | By June 2020 | Network focal points, Ministries of Environment, Ministries of Health, Customs, UN Environment ROLAC, UNECE, BRS Regional Centers | #### Resources for event logistics and travel |
| 3.3 Building capacities for the prevention and effective response of chemical accidents and spills | 3.3.1 Convene a face-to-face regional workshop with key stakeholders from the emergency reponse sector in each country to improve chemical accident and spill response | National institutions relevant to chemical accident and spill response are identified Improved capacities of accident and spill response personnel. | 12.4 3.8 and 3.9 | By October 2020 | Network focal points, Ministries of Environment, Ministries of Health, accident and spill response personnel, firemen, UN Environment ROLAC and Paris office. Private sector. | #### Resources for event logistics and travel |
|  | 3.3.2 To develop awareness raising material for response sector and the civil society (which can be used in the whole region) | Easy-to-follow videos, brochures, twitter messages about chemical accident and spill response | 12.4 3.8 and 3.9 16.6 | At least 2 videos (or other material) uploaded to the Network’s website by March 2020 | Network focal points with support of UN Environment ROLAC and Paris office | Resources to design, develop and upload the material Network website |
| 3.4 Identification and, where feasible, remediation of contaminated sites | 3.4.1 To host at least one webinar to share methodologies for sampling, analysis and remediation technologies of contaminated sites, as well as legal instruments related to contaminated sites | Existing methodologies and legal instruments have been disseminated in all sub-regions | 12.4 3.8 and 3.9 6.3 17.6 | 1 webinar by May 2020 | Network national focal points, UN Environment, Regional BRS Coordination Centers, RELASC | Countries willing to share their experiences Webinar platform |

| Topic 4: Basel, Rotterdam and Stockholm Conventions (BRS) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-topic | Cooperative actions | Milestones | SDG and target to which action contributes | Timeframe | Responsible/Partners | Resources required |
| 4.1 Implement Best Available Techniques (BATs) and Best Environmental Practices (BEPs) for activities with unintentional POPs emissions | 4.1.1 To hold a regional face-to-face workshop in cooperation with the BRS Secretariat to build capacties on BAT and BEP | Stakeholders from competent authorities and the private sector are trained on BAT and BEP | 12.4 3.8 and 3.9 17.6 | By November 2019 | UN Environment, BRS Secretariat, Network focal points, stakeholders from the private sector, BRS Regional Centers | Resources for workshop logistics |
|  | 4.1.2 To adapt the global BAT and BEP guidelines to the regional reality. In coordination with on-going/upcoming activities with the BRS Regional Centres. | BAT and BEP guidelines are “regionalized” (e.g. with specific case studies) | 12.4 3.8 and 3.9 17.6 | By December 2020 | Regional BRS Coordination Centers and BRS Secretariat, with support of the Network | Resources to work on adapting the guidelines |
|  | 4.1.3 To support the development of cooperation projects in countries (with a focus to review BAT/BEP available in the region) | At least 1 regional project proposal has been developed | 12.4 3.8 and 3.9 17.6 and 17.9 | By December 2020 | National focal points with support of UN Environment, BRS Secretariat, BRS Coordination Centers | Resources to devleop the proposal |
|  | 4.1.4 To hold a webinar to exchange experiences and lessons learned from projects implemented by countries of the region | Success projects have been replicated in other countries | 12.4 17.6 | 1 webinar in 2019 | UN Environment, BRS Secretariat, Network national focal points | Countries willing to share their experiences Webinar platform |
| 4.2 Build capacities to prevent illegal traffic of chemicals and waste | 4.2.1 To hold a webinar on main considerations to prevent illegal traffic of chemicals and waste, reduce main gaps in the region to prevent it, experiences from other regions | #### Gaps and opportunities to prevent ilegal traffic in the region are broadly discussed. Custom agencies have been reached as target audience. | 12.4 16.6 | 1 webinar by March 2020 | Network national focal points, UN Environment, Regional BRS Coordination Centers (Argentina), BRS and Minamata Secretariats | Countries willing to share their experiences Webinar platform |

| Topic 5: Mercury and Lead |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-topic | Cooperativeactions | Milestones | SDG and target to which action contributes | Timeframe | Responsible/Partners | Resources required |
| 5.1 Management of mercury waste (collection, storage, treatment, disposal), giving special attention to waste products containing mercury | 5.1.1 To hold a regional face-to-face workshop in cooperation with the Minamata Secretariat to disseminate and discuss on suitable alternatives for the management of mercury waste in the region and to share lessons learned about the implementation of Best Avaialble Techniques (BAT) and Best Environmental Practices (BEP) | The challenges and opportunities on the management of mercury waste in the region is broadly discussed and next steps are agreed among countries. Partnerships and agreements are also promoted among producers and transport sector. | 12.4 3.8 and 3.9 | By December 2019 | UN Environment, Minamata Secretariat, BRS Secretariat, Network focal points, Ministries of Environment, Ministries of Health, Municipalities | Resources for workshop logistics |
|  | 5.1.2 Identify funding for projects for the sound management of mercury waste in the region | At least 1 project proposal has been developed | 12.4 3.8 and 3.9 | By March 2020 | Network focal points with support of UN Environment | Resources to develop the proposal |
| 5.2 To support actions to reduce and, when feasible, eliminate the use of mercury in ASGM and in priority activities | 5.2.1 To facilitate the access and exchange of information on alternatives to mercury use in ASGM identified by different projects and initiatives in the region. | Information on alternatives for mercury use in ASGM are broadly disseminated (this may be done through the Regional Centers and the Global Mercury Partnership website) | 12.4 3.8 and 3.9 6.3 17.6 | By February 2020 | BRS Regional Centers Global Mercury Partnership Minamata Convention Secretariat | Global Mercury Partnership website and other means to disseminate the information |
| 5.3 Establish/strengthen mechanisms to control legal and illegal trade of mercury | 5.3.1 Support the development of national and regional assessments on legal and ilegal trade of mercury | The assessments provide new evidence where legal and ilegal trade of mercury are happening in the region | 12.4 16.6 | By November 2019 | Network focal points with support of UN Environment and Minamata Convention Secretariat | Resources to develop the assessments Resources to disseminate the assessments |
|  | 5.3.2 To develop a training activity with the authorities responsible for the control of mercury trade (including customs), to enhance capacity and international cooperation | A webinar on the use of mercury trade provisions and flows is developed A face-to-face regional or sub-regional workshop on mercury trade is organized The baseline for a regional cooperation strategy to avoid illegal traffic of mercury is prepared. | 12.4 16.6 | By December 2020 | Network focal points, private sector, national customs officers, with support of UN Environment and Minamata Convention Secretariat, and BRS Regional Centers | Resources for training logistics and design |
|  | 5.3.3 To compile a list of authorities and contact/focal points responsible for the authorization of mercury trade in the LAC countries | A list of contacts/focal points is gathered and made available to the LAC countries | 12.4 16.6 | By December 2019 | Network focal points, with support of UN Environment and BRS Regional Centers |  |
| 5.4 Improve public knowledge and awareness on health and environmental impacts of one of these priority substances (mercury/lead) | 5.4.1 Develop and implement a public education and awareness campaign on the health and environmental impacts of mercury/lead | Information on health and environmental impacts of mercury/lead is broadly disseminated | 16.7 | Throughout 2019-2020 | Network focal points, relevant ministries and partners, PAHO, NGOs | Resources to design and implement the campaign |
| 5.5 To support actions for a sound management of lead in products | 5.5.1. To facilitate the information exchange about experiences on the sound management of lead-acid batteries | Management of batteries is incorporated under the Extended Producer Responsibility (EPR) approach | 12.4 6.3 17.6 | 2019 - 2020 | Network focal points, private sector, customs, UN Environment, BRS Regional Centers | Website of the BRS Regional Centers and other dissemiantion mechanisms |
|  | 5.5.2 To hold a webinar/workshop/conference about progress made in the region to develop regulations for the elimination of lead in paints | Countries of the region develop regulation proposals for elimination of lead in paints | 12.4 16.6 17.6 | 2019 - 2020 | Network focal points, private sector, customs, UN Environment, BRS Regional Centers | Webinar platform |

| Topic 6: Waste management |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-topic | Cooperative actions | Milestones | SDG and target to which action contributes | Timeframe | Responsible/Partners | Resources required |
| 6.1 Develop systems to measure and characterize waste generation, including hazardous waste, keep up to date national waste inventories, and enhance waste management schemes | 6.1.1 Convene a series of webinars on (i) waste inventories and lessons learned from other regions, (ii) regulations and technologies in countries for waste treatment (for different types of waste, including electronic waste), and (iii) the Basel Convention Technical Guidelines on different waste streams, (iv) principles of minimization, recovery and integrated management of waste under sustainable approaches,. | At least 4 webinars delivered | 12.4 16.7 | 2 webinars in 2019 2 webinar in 2020 | Network national focal points, UN Environment, UNIDO, Regional BRS Coordination Centers, BRS Secretariat | Countries willing to share their experiences Webinar platform |
| 6.2 Good practices and best technologies to implement integrated management of hazardous waste (e.g. e-waste, mercury surplus and waste, used oils, used lead acid batteries, biomedical waste, and obsolete highly hazardous pesticides) | 6.2.1 To promote public-private regional partnerships to promote and implement extended producer responsibility schemes or systems on waste. Lead by countries with experience. | A public-private network is promoted and it participates in an awarness-raising campaing on producer responsibility | 12.4 17.6 and 17.17 | Throughout 2019-2020 | Network focal points, Regional BRS Coordination Centers, BRS Secretariat, UN Environment, key private sector stakeholders | Resoruces to design the campaign and host the public-private partnership |
|  | 6.2.2 To facilitate study tours on hazardous waste management to different countries | At least 2 countries are identified to share their experiences in study tours | 12.4 17.6 and 17.17 | Throughout 2019-2020 | Network focal points, officers from national competent authorities on hazardous waste management, Regional BRS Coordination Centers, BRS Secretariat, UN Environment, | Countries willing to share their experiences and host the study tours Resources to bring visitors to the study tour |

# Contributions to the implementation of the 2030 agenda

The implementation of this Action Plan will assist countries in the region in the achievement of the relevant Sustainable Development Goals (SDGs) and their respective targets under the 2030 Agenda. A key SDG that will be addressed under this Plan is SDG 12, “Ensure sustainable consumption and production patterns”, specifically target 12.4 of “By 2020, achieve the environmentally sound management of chemicals and waste throughougt their life cycle, in accordance with agreed international frameworks, and significantly reduce their releases to air, water and soil in order to minimize their adverse impacts on human health and the environment”. By contributing to an improved management of chemicals and waste in the Latin America and Caribbean region, the Plan intends to move forward the 2020 goal of the global agenda.

In addition to SDG 12, the Plan will also contribute to SDG 3 and SDG 6, “Ensure healthy lives and promote well-being for all at all ages” and “Ensure availability and sustainable management of water and sanitation for all”, respectively. Several cooperation actions under the Plan are targeted to improve capacities in the region to control pollution from chemicals and waste to air, water and soil. By doing so, these actions contribute to reduce the number of deaths and illnesses from hazardous chemicals and pollution (target 3.9) and to improve water quality by reducing that pollution (target 6.3). Moreover, the Plan also intends to improve capacities in the region in the health sector to address intoxications and health impacts from chemical exposure, which also contributes to SDG 3 by improving universal health coverage.

At the legislative and institutional levels, the Action Plan will promote cooperative actions in the region to strengthen the legal and institutional frameworks for improved enforcement of sound management of chemicals and waste. Through these actions, the Plan will not only contribute to improve capacities of countries to meet their commitments under the international multilateral environmental agreements (target 12.4), but will also improve accountability and transparency in institutions and ensure inclusive and participatory decision-making on chemical-related environmental matters (targets 16.6 and 16.7).

Last, but not least, the adopted approach of the Action Plan will promote the cooperation spirit of the SDG agenda under SDG 17 “Strengthen the means of implementation of the SDG agenda and revitalize the global partnership for sustainable development”, by enhancing South-South cooperation on knowledge, technology and innovation sharing to improve the sound management of chemicals in the LAC region.

# Resources for implementation

In order to effectively implement the Action Plan, the Network will determine the costs of the proposed actions, including the hosting of webinars, travel and accommodation of participants for face-to-face meetings, development of project proposals for submission to various funding agencies, development of the regional education and awareness-raising campaign and production of the relevant materials and tools, among others.

The Network’s Steering Committee has developed a Resource Mobilization Strategy (RMS). The main objective of the RMS is to ensure sustainable resources streams for the Action Plan and for the operation of the Network (ordinary and extraordinary meetings, coordination activities, Secretariat tasks, development of material for the Network and for dissemination, translation of documents and simultaneous interpretation of meetings, among others).

According to the estimations developed within the RMS, the resources that would be required to implement the proposed activities of the Action Plan 2019-2020, are indicated below:

| Topic | Estimated resources (USD) |
| --- | --- |
| Governance, coordination mechanisms and international presence | 20,800 |
| Knowledge, information and monitoring | 139,000 |
| Priority topics under the SAICM Global Plan of Action | 248,800 |
| Basel, Rotterdam and Stockholm Conventions | 94,800 |
| Mercury and Lead | 137,800 |
| Waste management | 37,600 |
| Total | 678,800 |

While the Network will strive to maximize in-kind contributions from countries and South-South cooperation within the region to mobilize these resources, a parallel effort will be undertaken to identify external funding from relevant donors (trust funds, development banks, UN agencies, bilateral donors, private sector), which will be necessary to implement the activities planned for the biennium, as well as to ensure the effective operation of the Network.

# Monitoring and follow-up

Monitoring of the Action Plan implementation will be undertaken as part of the tasks of the Network’s Steering Committee during its ordinary meetings, based on the milestones agreed in the Plan. The Steering Committee will submit half-yearly progress reports to the rest of national focal points of the Network for their approval.

A final achievements report will be prepared by the Steering Committee to be approved by national focal points and presented to the Forum of Ministers of Environment. The final report shall be approved by national focal points not later than two months before the end of the 2019-2020 biennium, in order for the Steering Committee to prepare for the next biennium’s Action Plan.

Annex I. Dates of ratification and entry into force of the international conventions of Stockholm, Rotterdam, Basel and Minamata in Latin America and the Caribbean

| Country | Stockholm Convention |  | Rotterdam Convention |  | Basel Convention |  | Basel Convention Ammendment | Minamata Convention |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Ratification, Accession (a) | Entry into force | Ratification, Accession (a) | Entry into force | Ratification, Accession (a) | Entry into force | Ratification, Acceptance (A) | Ratification, Accession (a) | Entry into force |
| Antigua and Barbuda | September 2003 | May 2004 | August 2010 (a) | November 2010 | April 1993 (a) | July 1993 | September 2016 (A) | September 2016 (a) | August 2017 |
| Argentina | January 2005 | April 2005 | June 2004 | September 2004 | June 1991 | May 1992 | September 2011 | September 2017 | December 2017 |
| Bahamas | October 2005 | Janunary 2006 |  |  | August 1992 | November 1992 |  |  |  |
| Barbados | June 2004 (a) | September 2004 |  |  | August 1995 (a) | November 1995 |  |  |  |
| Belize | January 2010 | April 2010 | April 2005 (a) | July 2005 | May 1997 (a) | August 1997 |  |  |  |
| Bolivia | June 2003 | May 2004 | December 2003 (a) | March 2004 | November 1996 | February 1997 | March 2005 | January 2016 | August 2017 |
| Brazil | June 2004 | September 2004 | June 2004 | September 2004 | October 1992 (a) | December 1992 |  | August 2017 | August 2017 |
| Chile | January 2005 | April 2005 | January 2005 | April 2005 | August 1992 | November 1992 | August 2009 (A) | August 2018 | November 2018 |
| Colombia | October 2008 | January 2009 | December 2008 | March 2009 | December 1996 | March 1997 | June 2014 |  |  |
| Costa Rica | February 2007 | May 2007 | August 2009 | November 2009 | March 1995 (a) | June 1995 |  | January 2017 | August 2017 |
| Cuba | December 2007 | March 2008 | February 2008 | May 2008 | October 1994 (a) | January 1995 |  | January 2018 (a) | April 2018 |
| Dominica | August 2003 (a) | May 2004 | December 2005 (a) | March 2006 | May 1998 (a) | August 1998 |  |  |  |
| Dominican Republic | May 2007 | August 2007 | March 2006 (a) | June 2006 | July 2000 (a) | October 2000 |  | March 2018 | June 2018 |
| Ecuador | June 2004 | September 2004 | May 2004 | August 2004 | February 1993 | May 1993 | March 1998 | July 2016 | August 2017 |
| El Salvador | May 2008 | August 2008 | September 1999 | February 2004 | December 1991 | May 1992 | December 2015 | June 2017 (a) | August 2017 |
| Grenada |  |  |  |  |  |  |  |  |  |
| Guatemala | July 2008 | October 2008 | April 2010 (a) | July 2010 | May 1995 | August 1995 | December 2013 |  |  |
| Guyana | September 2007 (a) | December 2007 | June 2007 (a) | September 2007 | April 2001 (a) | July 2001 |  | September 2014 | August 2017 |
| Haiti |  |  |  |  |  |  |  |  |  |
| Honduras | May 2005 | August 2005 | September 2011 (a) | December 2011 | December 1995 | March 1996 |  | March 2017 | August 2017 |
| Jamaica | June 2007 | August 2007 | August 2002 (a) | February 2004 | January 2003 (a) | April 2003 | September 2015 | July 2017 | August 2017 |
| Mexico | February 2003 | May 2004 | May 2005 (a) | August 2005 | February 1991 | May 1992 |  | September 2015 | August 2017 |
| Nicaragua | December 2005 | March 2006 | September 2008 (a) | December 2008 | June 1997 (a) | September 1997 |  | October 2014 | August 2017 |
| Panama | March 2003 | May 2004 | August 2000 | February 2004 | February 1991 | May 1992 | October 1998 | September 2015 | August 2017 |
| Paraguay | April 2004 | June 2004 | August 2003 | February 2004 | September 1995 (a) | December 1995 | August 1998 | June 2018 | September 2018 |
| Peru | September 2005 | December 2005 | September 2005 | December 2005 | November 1993 (a) | February 1994 | March 2015 (A) | January 2016 | August 2017 |
| Saint Kitts and Nevis | May 2004 (a) | August 2004 | August 2012 (a) | November 2012 | September 1994 (a) | December 1994 |  | May 2017 (a) | August 2017 |
| Saint Lucia | October 2002 (a) | May 2004 |  |  | December 1993 (a) | March 1994 | January 2002 |  |  |
| Saint Vincent and the Grenadines | September 2005 (a) | December 2005 | October 2010 (a) | January 2011 | December 1996 (a) | March 1997 |  |  |  |
| Suriname | September 2011 | December 2011 | May 2000 | February 2004 | September 2011 | December 2011 |  | August 2018 | November 2018 |
| Trinidad and Tobago | December 2002 (a) | May 2004 | December 2009 (a) | March 2010 | February 1994 (a) | May 1994 | January 2000 |  |  |
| Uruguay | February 2004 | May 2004 | March 2003 | February 2004 | December 1991 | May 1992 | March 1999 | September 2014 | August 2017 |
| Venezuela | April 2005 | July 2005 | April 2005 (a) | July 2005 | March 1998 | June 1998 |  |  |  |

Members of the Steering Commitee for the period when this Action Plan is developed are: Costa Rica, Mexico, Jamaica, Dominican Republic, Colombia, Peru, Brazil and Uruguay.

The Working Group is comprised of members of the Steering Committee and representatives of the six Regional and Subregional Coordinating Centers for the Basel and Stockholm Convention.

The survey and results of the survey can be found here in the report prepared by the Steering Committee.

This analysis takes into account those chemicals considered under the Strategic Approach to International Chemicals Management (SAICM). It does not take into account products from the food industry, pharmaceutical products, narcotics or other psychotropic substances, radioactive material, chemical weapons or their precursors. It was developed through a review of the National Profiles on Chemicals and Waste Management of the region and the most recent National Implementation Plans for the Stockholm Convention, as per http://chm.pops.int/.

UNEP, 2013. Global Chemicals Outlook. United Nations Environment Programme, Nairobi, Kenya. (http://web.unep.org/chemicalsandwaste/sites/unep.org.chemicalsandwaste/files/publications/GCO_web.pdf)

World Bank, 2014. Mapping Enterprises in Latin America and the Caribbean. The World Bank Group. (https://www.enterprisesurveys.org/~/media/GIAWB/EnterpriseSurveys/Documents/Topic-Analysis/Mapping-Enterprises-LAC-Note.pdf)

Informative note by UN Environment to the Forum of Ministers of Environment of the LAC region, 2014

BCCC/SCRC and UNEP, 2014. Report: The Minamata Convention on Mercury and its implementation in the Latin America and Caribbean Region. (http://mercuryconvention.org/Portals/11/documents/publications/report_Minamata_LAC_EN_FINAL.pdf)

EExact text from the survey

http://chm.pops.int/Implementation/BATandBEP/Guidance/Overview/tabid/5121/Default.aspx