## Slide 1
A PRESENTATION BY:
Ministry of Environment Climate Change Disaster Management & Meteorology
Solomon Islands
Global Monitoring Plan Phase II Project –Mid-term Review Workshop
17th -18th September 2018, Brisbane

## Slide 2
Overview of the Project activities in Solomon Islands
Resources/Facilities Available
Progress until present
Challenges and possible solutions
Lessons learnt
GMP project's outcomes /benefit
Opportunities, collaborations and networks
Sustainability in monitoring and future expectations
Outline of Presentation

## Slide 3
Overview of Project Activities in Solomon Is
Air sampling
Water sampling
Human milk sampling
Sampling of matrices of national interest
Policy & Legislative framework –Draft NIP, NWMPC Strategy 2017-2026, Environment Act under review

## Slide 4
Human Resources-
  Environment Officers conduct samplings for ambient air & water + shipment of samples
  Health Officers to conduct human milk sampling
Logistics support-Office vehicle utilized when available
Political Support – Endorsement of National Waste Management & Pollution Control Strategy in 2017, Draft NIP to be submitted for cabinet endorsement
Resources/Facilities Available

## Slide 5
Resources Utilized
Facilities
National Public Health Laboratory
- Tests for WQ covers e.coli, DO, salinity & arsenic but not for
POPs
Private Laboratory ( SPE Analytical)
- Soil sampling tests covers phosphorus, nitrogen, soil texture,
organic compounds, colouring & carbon but not on POPs.
- Water quality tests covers pH, conductivity, Dissolved oxygen,
salinity, e.coli but not heavy metals or POPs
Other Labs also exist but none of them does tests for POPs

## Slide 6
Progress until Present ( 2018)
GMP II National Inception held in 2016
Sampling sites identified in 2016
PUFs/Passive air sampling first installed in mid 2017
water samplings & passive air samplings conducted
Shipments of water samples & passive air samples done
SIHRERB committee approval to conduct breast milk sampling end of August 2018
National samplings- to be confirmed
Notes: SIHRERB- Solomon Islands Health Research Ethical Review Board

## Slide 7
Challenges & Solutions
Challenges | Solutions
Funding very restricted | Allow flexibility to support or enhance capacity and resources of national institutions
Coordination of multiple projects plus implementation of national priorities results in delays | Recruit dedicated person for coordination of project. Recruited person can then be absorbed by the Govt.
Logistics vehicle sometimes busy with other office tasks | Hire a taxi/vehicle to conduct the sampling

## Slide 8
Challenges | Solutions
Health (SIHRERB) Ethical Review Procedures | Ensure all paper work and requirements are presented to the committee
Lack of ability of National Labs to do laboratory work on POPs | Seek funding support to upgrade national laboratory
Support Officers are not familiar with sampling protocols | In-house training on sampling protocols
Shipment preparation & logistics can be time consuming | Prepare supporting paperwork for shipment a day ahead before shipment

## Slide 10
Lessons Learnt
Team work when conducting samplings to enhance each others capacity to do proper sampling
Coordination between stakeholders to maintain good networking & collaboration
Cross-check shipment paperwork by a second person ( ensure to include ‘no commercial value’ or 1 Euro dollar)
Preparation of shipment paperwork before date for shipment

## Slide 11
Project Outcomes /Benefits
Builds/strengthen the capacity of officers to monitor POPs concentration or to conduct proper sampling
Government officers better equipped with scientific or technical knowledge & tools to a high standard
Data collection on air, water , human exposure to POPs relevant for decision making /Policy /Legislation
Increased awareness of POPs exposure amongst stakeholders
Helps Government to provide inputs to the Stockholm Convention & to facilitate reporting

## Slide 12
Opportunities, Collaborations & Networks
Creates new networking through a multi-stakeholder approach
Builds on existing networking or coordination with stakeholders
Information dissemination and awareness

## Slide 13
Opportunities, Collaborations & Networks

## Slide 14
Sustainability & Future Expectations
Future Projects should have dedicated project officer
Flexibility of funding to support the capacity and resources of governments through:
  National Capacity building in MEAs
  Institutional strengthening
  Coordinate national initiatives/activities related to POPs
Harmonization of existing legislations to manage sound chemical management

## Slide 15
Sustainability & Future Expectations
Ownership & Sustainability - Results to be translated to ensure policy makers understand why the need for on-going monitoring. This can then be incorporated into National Planning & Budget
Harmonization of existing legislations to manage sound chemical management
Maintain POPs sampling sites
Separate Chemical Unit and Human resources to be responsible for Chemical Management within the MECDM

## Slide 16
Thank you for listening !
Tank iu tumas !