Draft for consideration at the subcommittee of the Committee of Permanent Representatives, 5 May 2022

The resumed fifth session of the United Nations Environment Assembly (UNEA-5.2):

ASSESSMENT AND LESSONS LEARNED

Prepared by the Secretariat of the UN Environment Programme.

This paper outlines observations, lessons learned and recommendations from the meetings of the resumed fifth session of the United Nations Environment Assembly (UNEA-5.2), held from 28 February to 2 March 2022, the Special Session to commemorate the 50th anniversary of the establishment of the United Nations Environment Programme (UNEP@50) held on 3 and 4 March 2022, the resumed fifth open-ended meeting of the Committee of Permanent Representatives (OECPR-5.2), held from 21 to 25 February 2021, prepared by the Secretariat, taking into account views expressed by Member States and Major Groups and Stakeholders.

- Background

- The United Nations Environment Assembly (UNEA) is the world’s highest-level decision-making body on the environment within the United Nations system. It was created following a decision in June 2012 at Rio +20 with the objective to strengthen and upgrade the UN Environment Programme and ensure a more coherent system of international environmental governance, with a universal membership including all 193 UN Member States.

- UNEA meets biennially to:

  - set the global environmental agenda;

  - provide overarching policy guidance and defining policy responses to address emerging environmental challenges;

  - undertake policy review, dialogue and exchange of experiences;

  - set the strategic guidance on the future direction of the UN Environment Programme;

  - organize a multi-stakeholder dialogue; and

  - foster partnerships for achieving environmental goals and resource mobilization.

- Through its resolutions and calls to action, the Environment Assembly provides leadership and catalyzes intergovernmental action on the environment and addresses emerging issues. The Assembly is also the governing body of the UN Environment Programme.

- Prior to UNEA meetings, Major Groups and Stakeholders organize a Global Major Groups and Stakeholder Forum to strategize and consolidate their inputs to UNEA.

- The first, second, third and fourth sessions of UNEA in 2014, 2016, 2017 and 2019 tackled major environmental themes such as illegal trade in wildlife, environmental rule of law, financing the green economy, pollution, the Sustainable Development Goals, and delivering on the environmental dimension of the 2030 Agenda for Sustainable Development, and innovative Solutions for Environmental Challenges and Sustainable Consumption and Production, and adopted three ministerial declarations and numerous resolutions and decisions.

- Due to the COVID-19 pandemic, Member States decided that the fifth session of the UN Environment Assembly (UNEA-5) should take place in a two-step approach. The first session of UNEA-5 (UNEA-5.1) was held fully online on 22 - 23 February 2021, and the resumed session of UNEA-5 (UNEA-5.2) took place in-person (hybrid format) in Nairobi on 28 February - 2 March 2022. The overall theme for UNEA-5 was “Strengthening Actions for Nature to Achieve the Sustainable Development Goals.

- A first UNEA Special Session to commemorate the 50th anniversary of the establishment of the United Nations Environment Programme took place in-person (hybrid format) on 3-4 March 2022, under the theme “Strengthening UNEP for the implementation of the environmental dimension of the 2030 Agenda for Sustainable Development.”

- The outcomes of UNEA-5.2 and UNEP@50 were prepared at by the resumed fifth open-ended meeting of the Committee of Permanent Representatives (OECPR-5.2), held 21-25 February 2022.

- UNEA-5.2 and UNEP@50 were held in-person, with strict COVID-19 protocols in place. These included mandatory daily rapid COVID testing, a cap on the size of delegations for Member States, Major Groups and Stakeholders and international organizations, limited access to meeting rooms through temporary badges to ensure social distancing, and mandatory wearing of masks. A full account of the COVID measures in place for the meetings is available in the Secretariat notification for UNEA-5.2 and UNEP@50.

- All meetings were also open to interactive online participation for delegates not in a position to participate in-person, or who would choose to participate virtually for any other reason. Accredited delegates participating online enjoyed full speaking and interpretation rights for all formal sessions through the meeting platform “Interactio”, and were offered the possibility to actively attend all negotiations taking place in dedicated working groups during OECPR-5.2 and the Committee of the Whole established by UNEA.5.2.

- The Secretariat conducted an online survey sent to all registered participants in mid-March 2022 with about 400 respondents representing a 8% response rate (for more information on registration see section IV). About half of the respondents were Member States delegates, and a quarter of the responses were provided by Major Group representatives. For almost all of the survey questions, the responses were overwhelmingly positive, indicating a 70-95% satisfactory rate. A detailed presentation of the results of the survey is available here.

- In accordance with UNEA decision 5/4, the sixth session of the Assembly will convene in Nairobi on 26 February to 1 March 2024, preceded by OECPR-6 to take place from 19 to 23 February 2024.

- Additional relevant background information is available here:

- UNEA main website

- Proceedings report of UNEA-5.2

- Outcomes from UNEA-5.1

- Outcomes from UNEA-5.2

- UNEA-5.2 key background documents

- Outcomes and background documents from UNEP@50

- Outcome of the Consensual Process for Review by the CPR (as endorsed at UNEA 5.2)

- UNEA Rules of Procedure

- Meeting Roadmap for the UN Environment Governing Bodies

II. Key outcomes from UNEA-5.2

- Key outcomes from the resumed fifth session of the United Nations Environment Assembly are:

- A ministerial declaration entitled “Strengthening actions for nature to achieve the Sustainable Development Goals”

- Adoption of the following resolutions:

  - UNEA resolution 5/1: Animal welfare environment and sustainable development nexus

  - UNEA resolution 5/2: Sustainable Nitrogen Management

  - UNEA resolution 5/3: Future of Global Environment Outlook

  - UNEA resolution 5/4: Sustainable Lake Management

  - UNEA resolution 5/5: Nature-based Solutions for supporting sustainable development

  - UNEA resolution 5/6: Biodiversity and Health

  - UNEA resolution 5/7: Sound Management of Chemicals and Waste

  - UNEA resolution 5/8: Science-Policy Panel to contribute further to the sound management of chemicals and waste and to prevent pollution

  - UNEA resolution 5/9: Sustainable and Resilient Infrastructure

  - UNEA resolution 5/10: Environmental dimension of a sustainable, resilient and inclusive post COVID-19 recovery

  - UNEA resolution 5/11: Enhancing Circular Economy as a contribution to achieving sustainable consumption and production

  - UNEA resolution 5/12: Environmental aspects of minerals and metals management

  - UNEA resolution 5/13: Due regard to the principle of equitable geographical distribution, in accordance with paragraph 3 of article 101 of the Charter of the United Nations

  - UNEA resolution 5/14: End plastic pollution: Towards an international legally binding instrument

- Adoption of the following decision:

  - UNEA decision 5/4: Provisional agenda, date and venue of the sixth session of the United Nations Environment Assembly

- Two leadership dialogues on the theme of UNEA-5, with active participation of high level representatives from Member States, Multilateral Environmental Agreements and other relevant organizations and stakeholders (more information here and here).

- One multistakeholder dialogue, allowing representatives of Major Groups and Stakeholders to interact with high level decision makers under the sub-theme “Building back greener: international environmental protection and achieving the Sustainable Development Goals in the context of the coronavirus disease (COVID-19) pandemic”.

- 51 recorded video statements and 44 written statements from Member States, international organizations, and stakeholders. All statements are available here.

- Based on a proposal from the Secretariat which was endorsed by the UNEA Bureau at its meeting on 8 December 2021, 22 official side events were organized at UNEA-5.2 and UNEP@50. Eight of these side events were in-person / hybrid “flagship” events organized at the meeting location, while 14 side events took place fully online. In addition, Major Groups and Stakeholders organized 17 unofficial side events in the “Green Room”.

- UNEA-5.2 pre-session working documents.

- UNEA-5.2 pre-session information documents.

III. Key outcomes from UNEP@50

- Key outcomes from the Special Session to commemorate the 50th anniversary of the establishment of the United Nations Environment Programme are:

  - A political declaration to commemorate the fiftieth anniversary of the establishment of the United Nations Environment Programme.

  - A report of the Executive Director on the science-policy interface, entitled “Reflecting on the past and imagining the future: a contribution to the dialogue on the science-policy interface”

  - Two leadership dialogues under the themes “Looking back: 50 years of UNEP” and “Looking forward: Achieving the 2030 Agenda for Sustainable Development for people and planet”, held on 4 March 2022.

  - One multistakeholder dialogue under the theme “Strengthening UNEP for the implementation of the environmental dimension of 2030 Agenda for Sustainable Development”, held on 4 March 2022 and informed by the Major Groups and Stakeholders report “The UNEP We Want”.

  - 108 recorded video statements and 12 written statements from Member States, international organizations, and Major Groups and Stakeholders.

  - UNEP@50 pre-session working and information documents.

IV. Participation and registration

- Statistics from the registration platform Indico provide the following information for UNEA-5.2 and UNEP@50:

- 169 Member States were registered, of which 147 Member States were represented in-person and 22 Member States online

- 5199 meeting delegates (of which 2396 were Member State delegates) were approved, with 3653 attending in-person and 1546 attending online; this is more than previous UNEA sessions where for example UNEA-4 saw 4942 approved participants incl 1713 Member States delegates.

- 10 Heads of State and Government / Deputy Heads of State and Government attended either of the meetings

- In total, 147 Member States participated at ministerial level (90 Ministers and 17 Vice Ministers in-person; 40 Ministers/Vice Ministers attended online); this is the highest number of Ministers attending a UNEA session to date.

- Concerns related to registration include late registrations, and a complex registration format on Indico due to the separation of in-person and online delegates and many different categories, resulting in complications and extra work for UNEP staff.

Lessons learned and recommendations for future online or hybrid UNEA or CPR meetings:

- Continue to initiate online registration early to avoid registration bottlenecks and delays.

- Simplify the registration portal to maximize its user-friendliness.

- Share adequate instructions and information on the registration procedure to all Member States and Major Groups and Stakeholders in a timely manner.

- Explore use of alternative registration platforms e.g. the e-registration portal on the e-delegate platform used by Member States at the UN Headquarters in New York.

V. Challenges and opportunities stemming from the organization of hybrid meetings

- UNEA-5.2, UNEP@50 and OECPR-5.2 demonstrated that organizing hybrid meetings, whereby all Member States and stakeholders are invited to attend in-person but with the choice to attend online both for negotiations and for the formal session is challenging but possible. No concerns were raised by Member States relating to hybrid format regarding transparency, inclusivity and universal participation.

- The in-person format of the meetings was paramount as a condition for the successful outcomes achieved from UNEA-5.2 and UNEP@50, as well as for the high level of participation.

- The hybrid format of the meetings and negotiations was well supported by online infrastructure, including online availability of key documents, effective communication of information from the Secretariat, and the use of the UNEA papersmart portal for the management of the draft resolutions in a safe IT environment.

- While future technology developments will likely make it easier to organize hybrid meetings, this will inevitably pose an additional workload and requires a different skillset for the Secretariat.

- Benefits from hybrid or online meetings with limited or no in person participation include:

- Participation of delegates who may not have the opportunity to attend in-person, including delegates who are not represented in Nairobi, and Major Groups and Stakeholders;

- Putting all countries, including those with small delegations, on a more equal footing regarding number of participants;

- Increased flexibility and simplicity to attend meetings e.g. by minimizing the time needed for transportation;

- Significantly lower environmental footprint due to limited travel;

- Cost savings due to limited travel and accommodation costs.

- Remaining challenges relating to hybrid or online meetings with limited or no in-person participation include:

- Occasional (often temporary) inability for Member States and Major Groups and Stakeholders to take the floor, for example due to instable internet connections or technological shortcomings;

- Internet or power cuts in the meeting room;

- Limited personal contacts among delegates, undermining necessary trust and limiting “corridor diplomacy”;

- “Screen fatigue”, creating a challenging work environment for delegates during long online sessions;

- Possible challenges relating to formal adoption of decisions/resolutions, including by voting (which is rare in the UNEA context);

- Working odd hours due to different time zones for delegates joining from far.

Lessons learned and recommendations for future hybrid and online UNEA or CPR meetings:

  - Organize UNEA-6 as an in-person (hybrid) meeting with a strong online component, while not excluding that some preparatory meetings may take place fully online, provided that they focus on information-sharing or informal consultations and do not involve formal decision-making.

  - Make optimal use of the intersessional period between the annual subcommittee meeting of the Committee of Permanent Representatives, where an initial consultation and scoping exercise should take place on possible draft resolutions, and the open-ended meeting of the Committee of Permanent Representatives where the drafts will be subject to final negotiations. During this period, in-depth consideration of the draft resolutions should be facilitated by organizing meetings under CPR subcommittee to allow for initial presentations by the proponents, followed by dedicated question-and-answer sessions.

  - Follow the guidance in the paragraphs 5 and 13 of the Outcome of the Consensual Process for Review by the CPR, including with regard to avoiding more than two parallel negotiations taking place at any given time, as well as the recommended deadline to announce draft resolutions at least 12 weeks in advance of UNEA, and to submit them at least 10 weeks in advance.

  - Apply reliable and use-friendly online platforms that ensure full simultaneous interpretation in official UN languages when required and allow for organizing parallel meetings and side events.

  - Continue to use and improve user-friendliness of the UNEA papersmart portal and explore alternative options for screen editing also based on practice from other intergovernmental bodies, to facilitate resolution negotiations.

  - Allocate sufficient human resources from the secretariat as well as the contracted online platform provider to ensure that adequate technical support is provided to delegations in advance as well as during the meetings, including direct assistance to delegations encountering technical problems as needed.

  - Ensure as far as possible that all delegates participating online use stable internet connections, apply the appropriate the browser compatible with the online meeting platform and a headset with inbuilt microphone.

  - Offer in-person and/or online trainings for delegates well in advance pf UNEA sessions to 1) familiarize themselves with the online meeting platform; 2) learn how to prepare draft UNEA resolutions and decisions; and 3) act as facilitators for negotiations.

VI. UNEA Documentation

- About than 95% of pre-session documents were issued on time and made available online in all official UN languages at least 6 weeks ahead of online UNEA-5.2 and UNEP@50. Many of them were prepared already in advance of UNEA-5.1 and remained relevant as background documentation.

- Due to the shortened time frame for UNEA-5.2 (3 days) compared to a regular UNEA session (5 days), in-session translation was only possible for the resolutions that were agreed at OECPR-5.2

- Post-session documents (edited and translated resolutions and meeting reports) were significantly delayed up to the end of April, due to a high workload for the UN Office in Nairobi because several other meetings took place immediately after UNEP@50.

- The technical assessment notes on the draft resolutions, outlining estimated costs for implementation, a legal opinion and an analysis of how the proposal relates to UNEP´s Programme of Work provided useful background information for the negotiations.

Lessons learned and recommendations for future online or hybrid UNEA or CPR meetings:

- Further improve the quality assurance process for pre-session UNEA documents, including by assigning experienced staff members to lead the process internally and by strategic planning and division of work at an early stage

- Continue the preparation of Secretariat technical assessment notes on draft resolutions in a timely manner.

- Plan and organize in-session documentation to ensure as far as possible that documents ready for adoption are translated to all official UN languages.

- Minimize any time lag for post session editing and translation of adopted resolutions and decisions.

VII. Preparations at regional levels

- Hybrid preparations at regional level, including through regional and subregional Ministerial Fora and other regional preparatory meetings, often organized back to back with regional Major Groups and Stakeholders consultations, contributed greatly to the success of UNEA-5.2, but there is a potential to create even stronger links between the national, regional and global levels in the preparations for UNEA meetings, with the support of UNEP´s Regional Offices.

Lessons learned and recommendations for future online or hybrid UNEA or CPR meetings:

- Capitalize on the various regional and subregional ministerial fora and other regional preparatory meetings, including those organized by Major Groups and Stakeholders, to promote effective regional contributions to UNEA;

- Make better use of the UNEP Regional Offices as “UNEA regional hubs” that can support national and regional preparations for future UNEA meetings.

- Facilitate early planning for participation and engagement at regional level in preparation for future UNEA sessions.

VIII. Stakeholder participation

- The Global Major Groups and Stakeholder Forum (GMGSF) was self-organized online by Major Groups and Stakeholders prior to UNEA 5.2 and UNEP@50, with 656 participants connected worldwide, and 24,000 recorded visits on the GMGSF online platform. The Forum facilitated Major Groups to strategize and prepare their inputs to UNEA. Internal meetings were also held throughout the UNEA sessions in the “Green Room”, a space provided to Major Groups and Stakeholders by UNEP for their own use. A Major Groups Facilitating Committee helped coordinate stakeholder participation. A total of 17 unofficial Major Groups and Stakeholders hybrid side events were organized in the Green Room.

- Major Groups and Stakeholders welcomed that each of the nine Major Groups was given a dedicated speaking slot at the UNEA opening plenary and asked for this practice to be applied consistently at UNEA-related meetings.

- Some Major Groups and Stakeholders representatives expressed concern about the hybrid format and the limited access to meeting rooms due to COVID restrictions, arguing that this gives them less opportunity to enrich the intergovernmental decision-making process through making interventions and by proposing alternative approaches. Concerns were also raised about limited funding provided for their in-person participation at both UNEA 5.2 and UNEP@50.

Lessons learned and recommendations for future online or hybrid UNEA or CPR meetings:

- Improve the opportunities for accredited Major Groups and Stakeholders to participate actively and meaningfully in online or hybrid meetings, including by increasing the number of speaking slots for Major Groups representatives and their access to informal working group meetings.

- Continue to offer speaking slots to each of the nine Major Groups at future meetings, thus acknowledging that Major Groups and Stakeholders consists of nine distinct groups;

- Continue to provide a permanent conference facility for Major Groups for their own use before and during UNEA sessions.

- Explore options to make that multi-stakeholder dialogues more interactive.

- Provide additional funding for travel of Major Groups and Stakeholder to facilitate in-person participation in UNEA meetings.

IX. Media and communication

- To maximize the impact of the hybrid (in person and online) event, targeted efforts and resources were identified to enhance online outreach and press engagement of the events, based on the UNEA 5 and UNEP@50 communication strategies, to ensure appropriate outreach and impact.

- News media outreach:

- UNEA-5.2 garnered a significant amount of global press with 14,449 news articles published across 4,290 outlets in 156 countries and 51 languages.

- 321 Journalists were accredited, and 4 hybrid press conferences were held.

- 9 Press releases were issued, and 4 op-eds.

- The 2022 UNEP Frontiers Report “Noises, Blazes and Mismatches”, which was launched in conjunction with UNEA 5.2, resulted in 413 articles published in 335 outlets across 58 countries in 9 languages.

- Similarly, the UNEP Wildfires Report launch led to 2032 articles published in more than 1425 outlets globally across 87 countries in 19 languages.

- Social media outreach, from UNEP´s 28 social platforms in 8 languages:

- UNEA 5.2 social media had excellent post reach of about 8 million on English-language channels. This drove over 45,000 link clicks, 800,000 media views.

- UNEP@50 social media: Post reach was over 3 million on English-language channels, leading to 27,000 link clicks, 570,000 media views.

- In total, about 200 key individual events were streamed online in all 6 official UN languages and in Swahili, incl opening and closing plenaries, national statements, leadership dialogues and some side events.

- 24K viewed UNEP@50 Opening plenary online.

- Side events did well, with for example 70,000 online viewers of the side even on the World Environment Situation Room launch, and 7,200 online viewers for the side event on the UN Decade on Ecosystem Restauration.

- UNEA 5 and UNEP@50 websites

- There were 2 million visitors to the revamped UNEA 5.2 website, with the audience staying for 3 minutes on average.

- Over 62,000 visitors came to the UNEA 5.2 Featured Updates page

- The most read article “What you need to know about plastic pollution?’ had 24,237 views.

- The “Why Plastics?” video had 263,000 views, and was the most watched, followed closely by the “Plastics resolution announcement video that was viewed 212,000 times.

- 3 News packages were posted to UNIFEED, these were broadcast 181 times by 48 international broadcasters.

Lessons learned and recommendations for future online or hybrid UNEA or CPR meetings:

- Prepare user friendly websites, with high quality audio visual content and a sophisticated social media strategy to drive visitors to the website.

- Time the launching of strategic UNEP reports to attract global media attention.

- Pre-produce written, multimedia and social assets to push through breaking news about UNEA and the resolutions that were gaveled.

- File video clips to UN headquarters newswire UNIFEED to bring international attention to UNEA and its resolutions.

X. Looking ahead towards the sixth session of the United Nations Environment Assembly

- Hybrid meeting formats (a combination of online and in-person participation), is likely to continue also after the COVID-19 pandemic. UNEP as the leading environment entity in the UN should continue to play a leading role in the organization of hybrid meetings, with the aim of finding an optimal balance between in-person and online meetings, thus seeking “the best of two worlds”.

- To ensure effective hybrid meetings, online meeting platforms must allow for the decision process to be transparent and inclusive, including through full interpretation services.

- Side-events for UNEP-led intergovernmental meetings may in principle be organized online, t’

- o benefit from increased flexibility and outreach, and lower financial and environmental costs.

- In some cases, especially for informal and/or consultative meetings (including at regional level), fully online meetings may be appropriate, with practical, environmental or financial benefits.

- Stakeholder meetings facilitated by UNEP may also increasingly be organized as hybrid meetings, with local participants meeting on-site while others connect virtually.

As set out in Governing Council decision 27/2