## Slide 1: 3rd Meeting of the 50th Anniversary Task Force
31 May 2016

## Slide 2: Task Force Teams Priority Tasks for May and June 2016
Team 3: EXPO & Main Event: Endorse additional invitees, finalize the EXPO agenda, and set-up, including from a content perspective
Team 5: 50th Publications: Commemorative book, documentary, SDG Roadmap, Brochures:
UNIDO-EU
UNIDO-China
UNIDO-GEF , etc.
Team 2: Timeline and Success Stories:
Agree on project showcases/success stories to be presented in the EXPO, events, publications, etc.
Team 4: Events around the world and field involvement:
Support field with articles by URs, events, involvement of academia and beneficiaries, etc.
Team 1: Sponsorship and Funds Mobilization:
Agree on funds mobilization process and detailed sponsorship package
TEAM HEADS NEED TO BE IDENTIFIED

## Slide 3: Team 1: Sponsorship and Funds Mobilization
Sponsorship package (in consultation with PRM, SDR, PMO, FIN), cleared by LEG, IOE
  Sponsorship options:
    EXPO Stands (L € 25,000 /M € 15,000/S €10.000)
    EXPO Side events (L € 15,000/M € 10,000/S € 5,000) and Events in the field (to be agreed with respective Regional/Field Office(s), depending on size) ,
    Documentary (min. € 5,000/€ 25,000) & Publications (€ 5,000 - €15.000)
    Voluntary contribution
  Benefits for our sponsors/partners:
    Exposure to an international audience
    Display of partner logo on the 50th anniversary web platform
    EXPO programme booklet, final brochures and “Partner Honour Wall”
    Online presence on Twitter, Facebook and Instagram (~70,000 followers)
  Additional benefits for premium partners:
    Speaking opportunity (3-5 minutes) during the main event and/or EXPO
    Invitation to VIP events and access to the VIP Lounge at the VIC during 21-25 November 2016
Sponsorship email (will be submitted to PMO for clearance today)

## Slide 4: Team 1: Sponsorship and Funds Mobilization
Way Forward: Sponsorship procedure (in consultation with PRM, SDR, PMO, FIN), cleared by LEG, IOE
Private Sector: CCM to inform vial mailshot (unless partners have responded to original invitation) PTC/Project Managers and CCM to engage with potential sponsors PRM to conduct risk commensurate due diligence SDR to follow up with donors wishing to contribute on funding arrangements | Monday, 6 June 2016 As of June 2016 As of July 2016 As of July 2016
b) Member States and Donors: Briefing to Permanent Mission by PMO and CCM PMO to share sponsorship package CCM to engage on matter of substance SDR to follow up with donors wishing to contribute on funding arrangements | Wednesday, 1 June As of June 2016 As of June 2016 As of July 2016
c) Development Finance Institutions: Approach individual technical DFI teams currently involved with UNIDO on specific initiatives to propose the idea of joint side events CCM to inform via mailshot PTC/Project managers and CCM to engage on matters of substance PRM to engage with specific technical teams, with PTC and DFI counterparts SDR to follow up with donors wishing to contribute on funding arrangements | As of June 2016 As of June 2016 As of June 2016 As of June 2016 As of July 2016

## Slide 5: Team 2: Timeline and Success Stories
Review design and set up of 50th web platform by Tuesday, 10 May 2016
Review and agree on the proposed project showcases/success stories to be presented via the web platform, EXPO, events, publications, etc. by Monday, 23 May 2016
Need to ensure that our selected project showcases tell a story.
Not only focus on the past, but also include the future direction for UNIDO and the linkages to the SDGs (incl. SDG Roadmap). Use anniversary celebrations as an opportunity to receive feedback on UNIDO’s future direction.
Work closely with Team 3 regarding the EXPO content and side events.

## Slide 6: Team 3: Main Event & EXPO, incl. Side Events
List of Invitees
Additional invitees with all PTC inputs reviewed and finalized
It is suggested that final review of list (already invited and additional ones proposed) must take into account regional balance, sector representation, etc.
  Gov/EUR (tot. 14): AUT 2, FRA 2, GER 9, RUS 2, SWE 1
  Gov/LAC (tot. 0)
  All (tot. 377): AFR (60), ARB (36), ASP (65), EUR (119), LAC (37), US-CAN (25)
  Bi Aid Agencies (tot. 5): SUI 2, FRA 1, AUT 2, KOR 1
35 high-level govt. invitees (Presidents 5, Prime Min. 2, Ministers 18) need to be taken care of. Support could be sought from the Austrian Ministry of Foreign Affairs.

## Slide 7: Team 3: Main Event & EXPO, incl. Side Events
EXPO Agenda
At this stage the Agenda needs to be kept as general as possible to accommodate for inputs still to be decided/confirmed (side events/keynote speeches, etc.) and updated accordingly
The 5 Ps are a strong portrayal of the EXPO must be highlighted in side events and possibly in keynote speeches and debates
During the IDB – 5/6 slots should be made available for videos
Interactive activities shall be considered (also based on DG’s proposal)
EXPO Agenda can be attached to the sponsorship packages until expert advice on EXPO management is brought on board
Gender and Youth must be reflected
How to best feature value chains/produced goods (considering time/location/theme)
Active contribution from all participants: tree, picture wall, etc.
EXPO is complex and ambitious and would benefit from expert/professional advice
Side events in parallel with the IDB??
Prioritization of speakers and side events

## Slide 8: Team 4: Events around the world & field
Articles on UNIDO-country relationship:
  EFR/RPF to send out request to 47 countries with URs incl. guidelines on Friday, 6 May 2016 - DONE
  EFR/RPF to receive articles by 31 May 2016: > 60% received (27 articles)
  EFR/RPF to select best articles by 14 June 2016
Involve academia in the field e.g. time capsules to be opened in 2030, develop awards – concept developed (cooperation with AEISEC)
Involve beneficiaries at events and produce video clips from beneficiaries by 30 June 2016
Design & prepare a communication package to be used at events (include posters, banners, and merchandise products) – Tuesday, 31 May 2016
Provide guidance on how to organize events on the occasion of the 50th in the field – mid June 2016 (cooperation with Project Managers)

## Slide 9: Team 5: 50th Publications
Commemorative book (including SDG roadmap):
  Draft outline and production schedule completed and distributed for comments
  Research to start immediately with available funding
  Authors: Peter Marsh/Steven Browne/Wilfried Luetkenhorst
  Reviewer: Sir Richard Jolly/Louis Emmerij /Thomas Weiss (EGM)
Documentary:
  Draft script produced (one pager)
  Request for information distributed among production companies (AP TV and LINX TV) and quotes obtained (others to be approached)
  Decision on funding and approach required
Publications to be promoted/prepared:
  EU-UNIDO Brochure (confirmation of updating pending)
  UNIDO-China Cooperation Brochure (first draft completed, second draft to be completed by June 10th)
  UNIDO-India Cooperation Brochure (will follow completion of China draft)
  UNIDO-GEF on the occasion of 25th anniversary (under preparation)
  Montreal Protocol (under consideration)
  ITPO Bahrain: Women Entrepreneurship (being edited, completion on June 17th)
Identify other possible publications which could be required
  Retirees book on industrialization in Africa (Africa Programmes)?