## Slide 1: Orientation: Writing for Assessments
Pierre Boileau (GEO Head)
Nov. 11, 2016

## Slide 2: GEO-6 Work programme
First global authors’ meeting
Second global authors’ meeting
Third global authors’ meeting + RE
Fourth global authors’ meeting
HLG SPM drafting meeting
MS SPM negotiation
UNEA-4
2017
2018
2019
May
February
March
UNEA-3
October
May
February
4-6 December
November
Acronyms: High Level Intergovernmental and Stakeholder Advisory Group (HLG),
Global Environment Outlooks (GEO), Summary for Policy Makers (SPM), Review Editors (RE)
Review Period
Review Period
October
Review editors meeting
1st Order Draft
Review Draft
Draft State and Trends with Policy Response
Progress Report to UNEA-3
Review Draft of full GEO
Final GEO-6
Author Draft of SPM
HLG Draft SPM
Final GEO-6 and SPM
Zero Order Draft
Notes: The GEO-6 work programme has been designed to deliver two separate review drafts, one for the first two parts of the document (State and Trends, Policy Response) and the second to deliver the full GEO-6 including outlooks. The meeting schedule will encourage authors to prepare the drafts at the appropriate times to ensure the process moves forward. Here are some details:
First author’s meeting in Feb. 2017 with all three main groups (State and Trends, Policy Response, Innovative Outllooks group) and the GEO-6 advisory bodies meeting. There will be parallel sessions and combined sessions to allow an appropriate level of interaction among the groups as well as allow them time to plan their individual activities. The Innovative Outlooks Group will outline the work they will do to develop new Outlooks methods and tools that will be used in GEO-6.
Second author’s meeting in May, 2017 with only the State and Trends and Policy Response groups meeting. Here the goal is to prepare a review draft of the first two chapters and to provide input to the progress report being prepared for UNEA-3.
Third author’s meeting, all groups come back together. Here the goal is to ensure the review drafts of the first two chapters are completed (State and Trends, Policy Response) and that the drafting begins for the Outlooks chapter. Review editors will be present here to ensure authors have dealt with review comments appropriately and to prepare their summary report of the review process. The HLG and SAP will meet to ensure adequate planning and also to finalize the progress report for UNEA-3.
Fourth author’s meeting, March, 2018. Here the goal is to prepare the review draft of the full GEO, including Outlooks. Authors will also prepare the first draft of the Summary for Policy Makers. HLG and SAP will meet for planning purposes but also to observe the author drafting process and ensure it’s credibility and relevance for the needs of Member States.
2nd Review Editor’s meeting will address review comments from the second review period and prepare a summary report of how these were dealt with.
HLG SPM drafing meeting will review the draft SPM prepared by the authors and prepare a review draft that Member States will receive.
Member State SPM negotiation meeting. The draft SPM will be finalized by Member States in preparation for endorsement by UNEA-4.
The full GEO-6 as well as the translated SPM will be made available to UNEA-4 for endorsement.

## Slide 3: Working Structure of GEO-6
Assessment Methodologies, Data and Information Group (AMDG)
High-level Intergovernmental and Stakeholder Advisory Group (HLG)
Scientific Advisory Panel (SAP)
UN Environment Secretariat
Co-chairs & vice-chairs
Coordinating Lead Authors
Lead Authors
Contributing Authors
State & Trends + Policy Response
Coordinating Lead Authors
Lead Authors
Contributing Authors
Innovative Outlooks Group
GEO Fellows
Review Editors
AMDG
Notes: The working structure of GEO-6 is different from GEO-5 in that it includes Co-chairs and vice-chairs. This structure was recommended by the Scientific Advisory Panel to help ensure the scientific credibility of the GEO-6 process. Other details of the structure include:
Policy advice will be received from the HLG
Scientific integrity of the process will be overseen by the SAP
Both advisory bodies will provide advice on the overall management of the GEO-6 process
The Co-Chairs (Dr. Ekin, Dr. Gupta) will act as the bridge between the advisory bodies and the author teams and will be supported by the Secretariat.
The Secretariat will continue to support the advisory bodies in their planning activities.
The author teams will be separated somewhat by the timing of the process, with the two first chapters being prepared in the first half of 2017 and the last chapter on Outlooks begin prepared in the last months of 2017 and the first months of 2018.
However, the main authors meetings will allow for interactions among all of the author teams in order to ensure coherence of the assessment.
GEO Fellows will support the process by assisting the authors with research questions and performing quality assurance tasks for citations and references.
Review editors will conduct evaluations at the end of each review period to ensure that review comments were dealt with appropriately. They will prepare a summary report from each review period.

## Slide 4: GEO-6 Timeline to February Meeting
Monthly HLG planning calls – timeline, deliverables, budget, policy approach etc.;
2 SAP planning calls – guidance to authors, ensuring scientific integrity, SAP interaction with Co-chairs, etc.
Regular Co-chairs calls (likely bi-weekly) – orientation, co-chair approach, working style with vice-chairs and Secretariat;
Face-to-face Co-chairs meeting in Bonn (mid-Oct.) – Overall GEO-6 planning + coordination with IPBES;
12 Authors calls – overall workplan and timeline + 5 orientation sessions (webinars) to prepare for February meeting.
Internal UNEP coordination meetings – core focal points for environmental themes and cross-cutting issues (Economics Division, Ecosystem Division, Law Division, SDGs, etc.)
Coordination meetings with science bodies (IPBES, IPCC, BRS, Ozone, etc.)
Authors
Advisory Bodies
Co-chairs & vice-chairs
November
December
2017
Oct. 20
Co-chairs call
Nov. 11
Writing for Assessments
Nov. 23 SAP
Webinar
Charts, Graphs, Maps
Secretariat
Conventions
Webinar
Citations, References
Oct. 24 HLG
Nov. 22
HLG
Nov. 5 Authors Selected
Webinar
SDGs & Indicators
Webinar
Matrix Drafting Approach
February
January
March
2017
Invitation
Alternate
Authors
GEO
Fellows
Jan. 31 HLG
SAP
Co-chairs
First Authors Meeting
Authors timeline
November
December
2017
Call
Authors
Land
Call
Authors
‘Outlooks’
Nov. 5 Authors Selected
Call
Authors
‘Biota’
February
January
March
Call
Authors
‘Air’
Call
Authors
‘Oceans/marine’
Call
Authors
‘Fresh water’
Call
Authors
‘Air’
Call
Authors
‘Fresh water’
Call
Authors
‘Oceans/marine’
Call
Authors
Land
Call
Authors
‘Biota’
Call
Authors
‘Outlooks’
First Authors Meeting
Oct. 28 Second Invitations
Oct. 21 First Authors Invitations

## Slide 5: Principle
Effective Assessments
Policy Relevant
Scientifically Credible
Data and Indicators
Based on analysis of existing research
Well referenced and summarized
Informs Policy Development
Accepted by user community
Timely information
Consolidation of knowledge from expert community
Succinct and to the point
Result
Avoid advocacy
Not policy prescriptive
Arguments are justified
Synthesis of findings
Independence of process
Balanced selection of authors and viewpoints
Respected data sources
Data tells a story
Justification is contained in references
No new research

## Slide 6: Example: Policy relevant but not policy prescriptive
“In order to ensure protection of land and marine biodiversity, more land reserves and marine protected areas must be created”
“Policy options for protecting land and marine biodiversity include: creating more land reserves and marine protected areas, acting on the demand-side for biodiversity resources…”
“Population growth and economic development will be significant over the coming decades, leading to more environmental degradation”
“Population is expected to grow by x% between 2015 and 2030, while gross domestic product is expected to grow by y%. These drivers could impact the environment in the following ways…”
Example: Scientifically credible

## Slide 7: Example: Data and indicators
“The fertility rate in the Asia-Pacific region is expected to decline and level out over the next decades (World Bank, 2012) ”

## Slide 8: Example: Based on existing research
Follows scientific publication methodology – Intro, Method, Results, Discussion, Conclusion
Extracts Conclusion and cites the relevant research that supports it.
“In many Latin American cities air quality exceeds the norms, which leads to many deaths.”
“In most cities exposure to PM2.5 exceeds the international recommended standards (Green and Sanchez 2012), and many deaths occur on account of diseases related to air pollution (WHO 2014c).”
Example: Well referenced and summarized

## Slide 9: Writing Style
Readable Assessments
Non-technical (where possible)
Examples, case studies
Graphics, charts, maps
Use new media – video, podcasts, interactive websites
Keep it short – only enough words to make your point
More take-up by non-scientists
Create a real-world feel to the findings
Picture is worth a thousand words
Reach community of influencers + teachers, students
Easily extractible – bite/byte size
Impact
Grade 6 level English
Easier to translate & understand
Space for more issues
Avoid reader fatigue
Clear results, no complicated
Easy to showcase
For visual learners
Ideal for social media
Creates demand for action
Reach a new audience

## Slide 10: Example: Non-technical language
“If temperature rises, many air pollution models project an increase in ground level ozone production, particularly in urban areas and surroundings (Hesterberg et al. 2009). Increased temperature also accelerates ozone destruction, and it is believed that the net direct impact of climate change on ozone concentrations around the world can be reduced (IPCC 2013).
“If temperature rises, many air pollution models show an increase in ground level ozone production, particularly in cities and surroundings (Hesterberg et al. 2009). Increasing temperature also speeds up ozone destruction, and it is thought that the effect of climate change on ozone levels around the world can be reduced (IPCC 2013).

## Slide 11: Examples and Case Studies

## Slide 12: Example: Graphs, charts and maps

## Slide 13: Example: New media
https://www.youtube.com/watch?v=0OiRvCkitYc

## Slide 14: Example: Keep it short
“However, current knowledge on the state of fish stocks in European seas should also be appraised on a sub-regional scale, because catches of commercially exploited species reveal strong sub-regional differences. For instance, most stocks of herring in the North Sea west of Scotland, and the Irish and Celtic Seas, are fished at or within maximum sustainable yield (MSY).”
“However, current knowledge on the state of fish stocks in European seas should also be appraised on a sub-regional scale, because catches of commercially exploited species show strong sub-regional differences. For example, most stocks of herring in the North Sea west of Scotland, and the Irish and Celtic Seas, are fished at or within maximum sustainable yield (MSY).”

## Slide 15: Questions ???